# Cascade Forge — All-Hands Meeting Minutes

Date: 12 February 2026

Location: Vancouver HQ, Boardroom A (with remote dial-in)

Attendees: Maya Chen (CEO), Daniel Park (CTO), Priya Iyer (CFO), Tomás Alvarado (VP Engineering), Hannah Brookes (VP Product).

# Agenda

1. Q1 2026 progress check.

2. Hiring plan update.

3. Legacy CLI sunset proposal.

4. Berlin office expansion budget.

5. Open discussion.

# Decisions

Approved hiring 6 additional engineers in Q2 2026, split as 4 backend engineers on the PulseDB ingest team and 2 frontend engineers on the Helix CI web UI team.

Decided to sunset the legacy Node.js CLI by 30 June 2026. The new Rust CLI ships as a static binary in May 2026. Customer comms will go out the week of 24 February 2026.

Allocated USD 400,000 for the Berlin office expansion, covering a second floor lease, furniture, and one new conference room. Work to be completed by end of Q3 2026.

Deferred a decision on opening a fourth office in São Paulo until the Q2 2026 board review.

# Action items

| Owner | Item | Due date |
| --- | --- | --- |
| Tomás Alvarado | Draft customer-facing migration guide for the new CLI. | 28 February 2026 |
| Sofia Reyes | Open the 6 Q2 engineering requisitions in the ATS. | 20 February 2026 |
| Priya Iyer | Wire the Berlin expansion budget to the Berlin entity. | 15 March 2026 |
| Hannah Brookes | Publish internal FAQ on the CLI sunset timeline. | 25 February 2026 |
| Daniel Park | Schedule the Q1 2026 architecture review for the platform team. | 10 March 2026 |

# Next meeting

11 March 2026, 10:00 PT.